## Form
Contract No.:
Contractor/Supplier's name:
Date of update:
|  |  | Shipment |  |  |  | Arrival at point of entry |  |  | Arrival at final destination(s) | [5 empty] | Comments
Consignment No.* | Commercial Invoice No. | Item No. (Goods details) | FOB/FCA Place | Transportation Method (by air/ocean/track/rail) : To be specified | ETD (Estimated time of departure) | ATD (Actual time of departure) | Point of entry name (airport/port/station/overland customs point) : To be confirmed | ETA (Estimated time of arrival) | ATA (Actual time of arrival) | Arrival at final destination(s) as per contractual Incoterm*
[10 empty] | Site XX (to be specified) |  | Site YY (to be specified) |  | Site ZZ (to be specified)
[10 empty] | ETA | ATA | ETA | ATA | ETA | ATA
1
2
3
4
*Add rows and/columns, if necessary.

## 【Sample】
Sample
Contract No.: XXXXX/1233456D/0001/001
Contractor/Supplier's name: ABC Corporation
Date of update: 20 May 2022
|  |  | Shipment |  |  |  | Arrival at point of entry |  |  | Arrival at final destination(s) | [5 empty] | Comments
Consignment No.* | Commercial Invoice No. | Item No. (Goods details) | FOB/FCA Place | Transportation Method (by air/ocean/track/rail) : To be specified | ETD (Estimated time of departure) | ATD (Actual time of departure) | Point of entry name (airport/port/station/overland customs point) : To be confirmed | ETA (Estimated time of arrival) | ATA (Actual time of arrival) | Arrival at final destination(s) as per contractual Incoterm*
[10 empty] | Ministry of Health |  | A Hospital |  | B Hospital
[10 empty] | ETA | ATA | ETA | ATA | ETA | ATA
1 | AA000001 | Item No.1 | Los Angeles | Ocean/Track | 2022-04-01 | 2022-03-28 | Dar es Salaam Port | 2022-05-01 | 2022-05-03 | 2022-05-30 | 2022-05-17 | 2022-05-30 | 2022-05-15 | 2022-05-30 | 2022-05-20
2 | AA000002 | Item No.1 (Spare parts) | Los Angeles | Air | Early June | TBC | Nairobi Airport | early June 2022 | TBC | 2022-06-30 | TBC | 2022-06-30 | TBC | 2022-06-30 | TBC
3 | AA000003 | Item No.2 Item No.3 Item No.4 | Dubai | Air/Track | 2022-05-01 | 2022-04-25 | Nairobi Airport | 2022-05-02 | 2022-04-26 | 2022-05-30 | TBC | 2022-05-30 | TBC | 2022-05-30 | TBC
4 | AA000004 | Item No. 5 Item No. 6 Item No. 7 | Yokohama | Ocean/Track | 2022-06-01 | TBC | Beira port | 2022-06-15 | TBC | 2022-06-30 | TBC | 2022-06-30 | TBC | 2022-06-30 | TBC
5 | To be confirmed (TBC) | Item No. 8 | Singapore | Air/Track | 2022-06-01 | TBC | Johannesburg Airport | early June 2022 | TBC |  |  |  |  | 2022-06-30 | TBC
6 | To be confirmed (TBC) | Item No. 8 (Spare parts) | Local supply | Track | End June 2022 | TBC | [7 empty] | 2022-06-30 | TBC
*Add rows and/columns, if necessary.
Note on G6: If specific schedule is fixed, please state it. If not, please state contractual delivery date.
Note on J6: If specific schedule is fixed, please state it. If not, please state estimated schedule.
Note on L8: If specific schedule is fixed, please state it. If not, please state contractual delivery date.
Note on R5: Please indicate in your comments if there are likely to be delays or problems from the contractual deadlines.